## Slide 1: 2018 general obligation bond authorization Measure LL
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Citizens’ Bond Oversight Committee District Financials from Inception through February 28, 2023
March 14, 2023

## Slide 2
The voters of the Lowell Joint School District authorized Measure LL General Obligation Bonds in the amount of $48,000,000 on November 6, 2018. Funds received from the bonds are to be used to:
Repair leaky roofs, old rusty plumbing and failing electrical systems
Replace wood and support beams that have extensive termite damage and dry rot
Renovate classroom facilities so they meet current building and safety standards
Remove hazardous materials like asbestos and lead paint from school sites
Upgrade classrooms, school facilities and technology to support high-quality instruction in math, science, technology and the arts
Improve student safety and campus security systems including security fencing, security cameras, emergency communications systems, smoke detectors and fire alarms
Improve heating, ventilation, air conditioning, insulation and doors to increase energy efficiency
Improve access to school facilities for students with disabilities
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Program Overview

## Slide 3
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Update
Maybrook Elementary – Interim Housing – Complete
Addition of Portable Classrooms and Restrooms
Lighting Upgrades
Site Work

## Slide 4
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Update
El Portal Elementary - Complete
Re-Roofing of Permanent Buildings
New Fire Alarm System

## Slide 5
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Update
Olita Elementary - Complete
Re-Roofing of Permanent Buildings
HVAC Replacement
Electrical Upgrades

## Slide 6
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Update
Macy Elementary – Complete
Re-Roofing of Permanent Buildings
HVAC Replacement
Electrical Upgrades
Fire Alarm
Sewer Repairs
Limited Storm Drain Repair

## Slide 7
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Updates
Jordan Elementary – Complete
Portable Replacement
Re-Roofing of Permanent Buildings
HVAC Replacement
Electrical Upgrades
New Fire Alarm
New Sewer Line

## Slide 8
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Update
Meadow Green Elementary Project
Meadow Green Elementary – In Progress
Re-Roofing of Permanent Buildings
HVAC Replacement
Electrical Upgrades
New Fire Alarm
Sewer Line Upgrades

## Slide 9
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Update
Meadow Green Elementary Project
Beam Repair - After
Beam Repair - Before

## Slide 10
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Update
Meadow Green Elementary Project
Classroom Chase
Roofing and HVAC

## Slide 11
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Future Projects

## Slide 12
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Future Projects
Maybrook Elementary (Est. Project Start April, 2023)
Addition of Portable Classrooms and Restrooms

## Slide 13
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Future Projects
Rancho Starbuck Intermediate (Est. Project Start June, 2023)
Re-Roofing of Permanent Buildings
HVAC Replacement
Electrical Upgrades
New Fire Alarm
New Sewer Line

## Slide 14
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL – Financial Update

## Slide 15
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Project Budgets & Expenditures
District Project Name | Project Budget per GBA Report 8/4/2020 | Project Expenditures to Date through 2/28/2023 | Difference | Comments
Maybrook Interim Housing Phases I&II | $3,750,000 | $3,352,536 | <$397,464> | Phase I 100% Complete. Certified by DSA Phase II awarded. Begins April, 2023
El Portal Re-Roofing | $2,617,713 | $2,324,921 | <$292,792> | 100% Complete. In to DSA for Certification
Olita Re-Roofing and HVAC | $5,657,936 | $5,071,808 | <$586,128> | 100% Complete. Certified by DSA
Macy Re-Roofing, F/A, and HVAC | $5,595,920 | $5,187,730 | <$408,190> | 100% Complete. Certified by DSA
Jordan Modernization | $14,552,815 | $12,057,516 | <$2,495,299> | 99% Complete $2M Funded by Bond, $1.4M by Dev. Fees
Meadow Green Re-Roofing and HVAC | $7,388,138 | $5,470,054 | <$1,918,084> | In Progress. 80% Complete
Rancho Starbuck Re-Roofing and HVAC | $12,200,000 | $941,767 | <$11,258,233> | Documents at DSA. Budget updated for seismic retrofit of library.
Districtwide Ad’s, Bidding, Pre-Qualification, Other |  | $734,053 |  | 
Combined District-Wide | $51,762,522 | $35,140,387 | $16,622,135 | 

## Slide 16
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
“Home of Scholars and Champions”
Measure LL Projected State Matching Funds
Measure LL Project Authorization |  | $48,000,000
Olita State Matching Funds Received (Fall 2021) |  | $3,404,000
Total Project Funds Available |  | $51,404,000
The District is in the process of applying for approximately $19 million in State Matching Grant Funds pending passage of a new state bond measure. Estimated wait is 4-8 years. |  | 
School Site | Pending/Projected State Matching Grants | 
Macy Elementary | $4,311,393 | 
Maybrook Elementary | Funding Unlikely | 
El Portal Elementary | $1,489,570 | 
Rancho Starbuck Intermediate | $6,561,553 | 
Jordan Elementary | $3,109,592 | 
Meadow Green Elementary | $4,454,043 | 
Total | $19,926,151 | 

## Slide 17
LOWELL JOINT SCHOOL DISTRICT
A Tradition of Excellence Since 1906
Questions